## Summary
CounselMate CRM Functional Roadmap
Generated from current repo status and PROGRESS.md
Current Focus | Sprint 8 Phase 1 is implemented and progress is marked: Hangfire PostgreSQL jobs, tenant-scoped in-app notifications, reminder scheduling, deduplication, retries, preferences, inbox UI/APIs, migration, and role boundaries are in place. User deferred final QA/testing.
Immediate Next | User will test Sprint 8 Phase 1 later. After that, the next planned build item is Sprint 8 Phase 2: email notifications provider adapter.
Hold Later Work | Email and WhatsApp remain disabled until Phase 1 QA/sign-off, provider configuration, consent/template requirements, and production secret rotation are complete.
Status Snapshot | Count
Completed | 5
Partially Done | 24
Not Started | 2
Next Priority | 1
Recommended Work Order
1 | Stabilize current workflows
2 | Activity communication templates
3 | Tenant profile/settings manual role QA
4 | Follow-up workspace manual role QA
5 | Lead import/export implementation
6 | Reports upgrade
7 | Documents
8 | Payments
9 | Automation/notifications
Last Updated | 2026-07-01 15:45

## Roadmap
Phase | Priority | Module | Feature / Workflow | Status | Completion % | Current Implementation | Missing / Gap | Next Action | Primary Roles | Testing Status
Foundation | 1 | Planning | Production scope, module plan, technical stack, QA/deployment notes | Completed | 100 | Scope docs, progress tracker, deployment notes, and UI reference review are in place. | Keep progress tracker updated after every functional milestone. | Update this roadmap after each completed sprint. | Owner, Developer | Verified by documentation review
Foundation | 1 | Frontend Shell | React/Vite app shell with sidebar, topbar, navigation, responsive base layout | Completed | 100 | Dashboard, Leads, Pipeline, Follow-ups, Counsellors, Reports, Settings routes/screens exist. | Needs final mobile polish pass after all modules settle. | Do one full mobile QA pass near release. | All roles | Build passing
Foundation | 1 | Backend/API | ASP.NET Core API, CORS, health endpoint, EF Core, PostgreSQL/Neon | Completed | 100 | API project, EF models, migrations, tenant-scoped data, Neon connection verified. | Production observability/logging still basic. | Add structured logs and deployment health checks before production. | System | Health endpoint healthy
Foundation | 1 | Multi-Tenant Database | Tenant, branches, users, courses, stages, sources, leads, follow-ups, activities | Completed | 100 | Tenant-aware schema and seed data are implemented and migrated. | Tenant billing/subscription boundaries not implemented. | Add subscription/billing only after core CRM is stable. | Owner/Admin | Migrations applied
Core CRM | 1 | Authentication | Login, logout, session restore, bearer token, current user | Completed | 100 | HMAC token auth, PBKDF2 passwords, current-user endpoint, frontend session restore. | Forgot-password is informational only; no email reset flow. | Add email reset when mail delivery is configured. | All roles | Smoke tested
Core CRM | 1 | Authorization | Owner/Admin/Counsellor/Read-only role-aware access | Partially Done | 85 | Backend blocks read-only writes; frontend hides/disables many actions; counsellor lead scope implemented. | Role matrix needs final UX pass so disabled reasons are always clear. | Add permission messages/tooltips and finish role-based UI audit. | All roles | Needs manual role QA
Core CRM | 1 | Dashboard | Tenant CRM overview and operational cards | Partially Done | 75 | Dashboard loads backend data and shows summaries/recent activity/schedule. | Metrics are still basic; advanced charts and actionable drilldowns are incomplete. | Add drilldowns after lead/follow-up workflows are finalized. | Owner/Admin/Counsellor/Read-only | Basic smoke tested
Core CRM | 1 | Lead Management | Add, list, search, filter, sort, edit, assign, archive/restore leads | Partially Done | 92 | Backend and frontend support lead CRUD, duplicate phone protection, filters, role scope, archive/restore, drawer detail, plus CSV/XLSX import preview/commit and filtered export for Owner/Admin. | UI needs final usability polish; bulk import/export needs manual browser QA with real client files before completion. | Run Sprint 4 manual QA, then move to reports upgrade after sign-off. | Owner/Admin/Counsellor | Builds passed; import/export API smoke tested; manual UI QA pending
Core CRM | 1 | Lead Detail Drawer | Profile, assignment, stage/status/priority, next follow-up, activity timeline | Partially Done | 85 | Lead detail opens from table/pipeline; profile update, notes, follow-up lifecycle, timeline exist. | Activities are embedded in drawer only; not yet a full communications workspace. Some controls need clearer disabled-state messaging. | Improve drawer layout and add communication templates next. | Owner/Admin/Counsellor | Needs focused UI testing
Core CRM | 1 | Pipeline | Kanban-style stage board for leads | Partially Done | 75 | Pipeline loads stages/leads; lead cards open drawer; Add Card now opens Add Lead with selected stage. | Drag-and-drop is not implemented; board/list/high-priority/due-today toolbar buttons are placeholders. | Implement real pipeline filters and optional drag/drop stage movement. | Owner/Admin/Counsellor/Read-only | Manual UI QA ongoing
Core CRM | 1 | Follow-up Lifecycle | Schedule, reschedule, cancel, complete follow-ups | Partially Done | 90 | Backend lifecycle, immutable completed/cancelled states, NextFollowUpAt recalculation, drawer controls, and actionable Follow-ups page queue exist. | Reminder notifications and background jobs are not implemented yet. | Manual role QA for Owner/Counsellor/Read-only, then move to activity communication templates. | Owner/Admin/Counsellor | Build passed; API smoke checked; manual role QA pending
Core CRM | 1 | Activities | Activity notes and timeline | Partially Done | 65 | Activity notes can be added from lead drawer and grouped in timeline. | No template library, no communication send logs, no WhatsApp/email integration, no standalone activity center. | Build activity communication templates as next main feature. | Owner/Admin/Counsellor | Basic API tested
Admin | 2 | Team Management | Tenant users, roles, status, branch assignment, reset password | Partially Done | 85 | User list/create/edit/reset password, filters, duplicate email checks, self-protection, admin/owner rules. | Invite flow and email delivery are not implemented. More role-specific UI messages needed. | Add user invitation/reset email later; do role QA first. | Owner/Admin | Smoke tested
Admin | 2 | Platform Tenant Onboarding | Owner creates client institute and tenant admin | Partially Done | 80 | Owner-only Platform page creates tenant, branch, admin, default stages/sources/courses; tenant admins can now maintain the persisted institute profile and defaults. | Subscription status and onboarding checklist are not implemented. | Complete tenant profile role QA, then design the onboarding checklist later. | Owner | Smoke tested
Admin | 2 | Master Data | Branches, courses, lead sources, lead stages | Partially Done | 90 | CRUD/deactivation, usage counts, uniqueness, optimistic concurrency, stage ordering/defaults. | Some advanced settings like custom fields, SLA rules, required-stage validations are not implemented. | Complete Settings role QA; advanced SLA/custom-field rules remain later scope. | Owner/Admin | Smoke tested
Admin | 2 | Tenant Settings | Institute profile, branding, contact details, preferences | Partially Done | 95 | Persisted institute profile supports contact details, address, timezone, logo URL, brand color, default branch, and default assignee. Owner/Admin edit controls, optimistic concurrency, validation, immediate sidebar branding refresh, and lead-form defaults are implemented. | Manual browser QA remains for Owner/Admin edit behavior and Counsellor/Read-only view-only behavior. File upload/storage for logos is not included; branding uses a validated HTTP/HTTPS URL. | Run the tenant settings role matrix and verify branding/defaults in the Add Lead flow, then mark completed. | Owner/Admin | Builds passed; two DB migrations applied; owner save/validation/concurrency/default API smoke tests passed; counsellor write returned 403; manual UI QA pending.
Productivity | 2 | Communication Templates | Reusable note/WhatsApp/email/call/demo/payment templates | Partially Done | 90 | Backend template CRUD, tenant-scoped communication_templates table, default templates, placeholder validation/rendering, Settings template manager, lead drawer template picker, and template-generated activity logs are implemented. | Manual role QA is pending. Actual external WhatsApp/email/SMS sending and delivery logs are reserved for Automation & Notifications. | Test Owner/Admin template CRUD, Counsellor template application on own leads, read-only restrictions, inactive templates, duplicate names, and invalid placeholders. | Owner/Admin/Counsellor | Build verified; DB migration applied; local API smoke passed for owner login + template list; manual role QA pending.
Productivity | 2 | Lead Import/Export | CSV/Excel import, duplicate handling, export filtered leads | Partially Done | 90 | CSV/XLSX import template download, file parsing, header mapping, row validation, duplicate skip/update mode, atomic commit, activity logging, filtered CSV/XLSX export, and Owner/Admin UI are implemented. | Manual browser QA remains for large files, mapping corrections, duplicate update/skip behavior, and final import commit using real sample data. | Run Owner/Admin Sprint 4 test matrix and fix any file-specific issues before marking completed. | Owner/Admin | Builds passed; Owner API smoke and counsellor 403 boundary tested
Productivity | 3 | Bulk Lead Actions | Bulk assign, bulk stage update, bulk archive | Not Started | 0 | No multi-select/bulk API. | Need table selection, backend bulk endpoints, audit activity logs. | Implement after import/export. | Owner/Admin/BranchManager | Not started
Productivity | 3 | Task/Reminder Workspace | My tasks, overdue, due today, upcoming | Partially Done | 75 | Follow-ups page now has queue tabs, search, priority filter, open lead, complete, cancel, and reschedule actions. | No notification reminders, calendar sync, or background alerting yet. | Manual role QA and later automation/notification implementation. | Owner/Admin/Counsellor | Frontend build passed; API smoke checked; manual role QA pending
Reports | 3 | Basic Reports | Conversion funnel and lead source/counsellor reporting | Partially Done | 45 | Reports screen and conversion endpoint exist. | Charts are basic/static in places; date filters, exports, role scoping, saved views missing. | Implement real report filters and export later. | Owner/Admin | Partially tested
Reports | 3 | Advanced Analytics | Cohort, counsellor performance, source ROI, stage aging | Not Started | 0 | No advanced analytics implementation. | Needs aggregated APIs, date ranges, comparison views. | Schedule after core CRM and import/export. | Owner/Admin | Not started
Admissions | 4 | Documents | Student document tracking and uploads | Partially Done | 95 | Cloudinary-backed document checklist, upload/replace, download proxy, verification/rejection, deletion, role permissions, metadata, and tenant-scoped migration are implemented. | Manual browser role QA remains; production hosting must receive Cloudinary environment variables and secrets must be rotated before release. | Run Owner/Admin/Counsellor/Read-only document QA and verify production Cloudinary configuration before marking completed. | Owner/Admin/Counsellor | Backend/frontend builds passed; Neon migration applied; manual browser QA pending.
Admissions | 4 | Payments | Fees, payment plans, reminders, receipts | Partially Done | 95 | INR fee records, immutable payment transactions, due dates, derived balances/statuses, receipts, activity logs, cancellation rules, concurrency, tenant scope, and Owner/Admin/Accountant management UI/APIs are implemented. | Manual browser/API role QA remains. Automated reminders and payment analytics/export belong to Automation and reporting follow-up work. | Run Owner/Admin/Accountant/Counsellor/Read-only payment QA, including overpayment, duplicate receipt, stale version, archived lead, and permission boundaries. | Owner/Admin/Accountant | Backend build passed with zero warnings; frontend production build passed after implementation; Neon migration applied; manual QA pending.
Admissions | 4 | Application/Enrollment | Application status, enrollment handoff, won/lost rules | Partially Done | 35 | Lead stages can mark won/lost and stage rules exist. | No dedicated application/enrollment entity or admission checklist. | Design after lead lifecycle is stable. | Owner/Admin/Counsellor | Not started as separate module
Automation | 5 | Notifications | Email/WhatsApp reminders, overdue alerts | Partially Done | 85 | Phase 1 implemented: Hangfire-backed tenant-scoped in-app notifications, follow-up/payment reminders, inbox/unread/read APIs and UI, preferences, deterministic deduplication, stale-state dismissal, retries, retention, status monitoring, and manual queue controls. | User deferred manual browser QA and disposable due-record tests. External email/WhatsApp adapters, credentials, delivery webhooks, consent, and provider-specific failure handling are not implemented. | When user testing is complete, fix any Phase 1 defects, then implement the email provider adapter as Phase 2. Keep WhatsApp last and feature-flagged. | Owner/Admin/Counsellor | Progress marked on 2026-07-01 15:45: backend Release build, Neon migration, Hangfire schema initialization, and API authorization/concurrency smoke tests passed; user browser QA pending.
Automation | 5 | Background Jobs | Scheduled reminders, stale lead alerts | Partially Done | 90 | Hangfire uses PostgreSQL storage with bounded workers, dedicated queues, recurring five-minute scans, distributed execution locking, bounded retries, retention cleanup, protected status, and manual run controls. | User deferred final job QA with disposable follow-up/payment data. Production deployment still needs worker/queue monitoring alerts and load testing at expected tenant volume. | Run final reminder creation/idempotency test with disposable data during QA, then configure production monitoring thresholds before release. | System | Progress marked on 2026-07-01 15:45: runtime initialization and manual job queue smoke test passed against Neon; disposable-data and load tests pending.
Automation | 5 | Audit Log | User-visible audit trail for sensitive actions | Partially Done | 45 | Lead activities record many lead events. | No global audit log for settings/users/platform changes. | Add audit trail before production/admin hardening. | Owner/Admin | Partial
Production | 6 | QA/Test Coverage | Manual QA matrix, API tests, UI smoke tests | Partially Done | 45 | Several smoke tests and builds have been run; progress tracker records them. | No automated test suite yet; no Playwright regression pack. | Create role-wise manual QA checklist and then automate critical paths. | Developer/QA | Manual only
Production | 6 | Deployment | Render backend, Vercel frontend, Neon database | Partially Done | 40 | Deployment notes exist and Neon is used. | Production env, secrets, domain, CORS, logging, migrations pipeline not fully finalized. | Deploy only after core workflows and role QA pass. | Developer/Admin | Not production deployed
Production | 6 | Security Hardening | Secrets, password reset, audit, rate limits, validation | Partially Done | 50 | Password hashing, bearer tokens, role checks, validation are implemented. | Need token refresh strategy, rate limiting, reset email, secret rotation, security headers. | Do security pass before production deployment. | System | Partial

## Execution Flow
Order | Milestone | Goal | Depends On | Status | Exit Criteria | Why This Order
1 | Stabilize Current Core | Make existing lead, pipeline, drawer, follow-up, activity, and role UI testable and predictable. | Current implementation | Next Priority | Owner/Counsellor/Read-only tests pass without confusing disabled/dead controls. | Prevents building new modules on top of unclear workflows.
2 | Communication Templates | Add reusable templates for notes, calls, WhatsApp, email, demo reminders, payment reminders. | Stable activity workflow | Partially Done | Implementation complete for template CRUD, variable rendering, lead drawer application, and activity logging. Manual role QA remains before marking completed. | Activities are already partially done; templates complete that functional area.
3 | Tenant Profile Settings | Persist institute profile, branding/contact/preferences/default rules. | Master data stable | Partially Done | Profile/contact/address/timezone/branding/default branch/default assignee persistence and UI are implemented. Manual role QA remains before completion. | Needed before onboarding real institutes.
4 | Follow-up Workspace Upgrade | Make Follow-ups page actionable, not just a list. | Follow-up lifecycle stable | Partially Done | Users can filter due/overdue/upcoming and complete/reschedule/cancel from Follow-ups page. | Daily work should happen from a task workspace, not only from lead drawer.
5 | Lead Import/Export | Bulk bring in leads and export filtered data. | Lead validation stable; tenant settings known | Partially Done | CSV/XLSX template, preview, validation, duplicate handling, atomic commit, filtered export, and UI are implemented. Manual browser QA must pass before completion. | Real client onboarding needs data migration.
6 | Reports Upgrade | Make reporting real and useful. | Stable leads/follow-ups/import data | Partially Done | Live date-filtered source/counsellor/stage reports and Owner/Admin exports are implemented. Manual browser QA and advanced chart polish remain. | Reports should reflect final data model and workflows.
7 | Documents | Track admission documents and verification. | Core CRM stable | Partially Done | Implementation and Neon migration complete; manual role QA and production Cloudinary configuration remain. | Admission workflows need docs after lead lifecycle.
8 | Payments | Track fees, due dates, receipts, reminders. | Documents/admission flow defined | Partially Done | Implementation and Neon migration complete; manual role QA remains; reminders move to Sprint 8. | Payment scope is larger and should not distract from core CRM.
9 | Automation | Background reminders, alerts, notification sending. | Templates and follow-up workflow | Partially Done | Phase 1 jobs and in-app delivery are implemented and API-smoke-tested; browser/disposable-data QA and external provider phases remain. | Automation depends on templates and task rules.
10 | Production Deployment | Ship stable app to Render/Vercel with Neon. | Core QA + security pass | Partially Done | Environment variables, migrations, CORS, logging, secrets, smoke tests complete. | Deployment before workflow stability creates avoidable rework.

## Role Testing
Role | Module | Should Be Able To | Should Not Be Able To | Current Status | Test Steps
Owner | Platform | Create tenants/institutes, view tenant list. | Nothing platform-related should be hidden from owner. | Partially Done | Login Rahul > Platform > create test tenant > login as tenant admin.
Owner | Leads | Create/edit/assign/archive/restore/search/filter/sort all tenant leads. | N/A for tenant leads. | Partially Done | Create lead > duplicate phone check > edit > archive > restore.
Owner | Pipeline | View all leads, add card, open lead, change stage via drawer. | N/A for tenant pipeline. | Partially Done | Pipeline > Add Card > save > open card > change stage.
Owner | Follow-ups | Schedule/reschedule/cancel/complete follow-ups. | Completed/cancelled follow-ups should not be mutable. | Partially Done | Open lead drawer > schedule > reschedule > cancel/complete.
Owner | Team | Create/edit users, reset passwords, manage roles except protected self/owner rules. | Self-deactivation should be blocked. | Partially Done | Counsellors > create user > edit > reset password > try duplicate email.
Owner | Settings | Manage branches/courses/sources/stages and reorder stages. | Should not break dependency rules. | Partially Done | Settings > each tab > add/edit/deactivate > test in-use conflict.
Admin | Leads/Team/Settings | Manage tenant CRM, users, and master data within admin rules. | Should not update owner accounts or access platform owner-only flows. | Partially Done | Create/login admin user > repeat owner tests except Platform and owner updates.
Counsellor | Dashboard | See scoped data for assigned leads. | Should not see all tenant leads. | Partially Done | Login S. Verma > dashboard numbers should reflect assigned scope.
Counsellor | Leads | Create leads assigned to self, edit own assigned leads, add activities/follow-ups. | Assign to other counsellors, archive/restore, manage users/settings/platform. | Partially Done | Login S. Verma > Add lead > open own lead > edit > schedule follow-up > add note.
Counsellor | Pipeline | See assigned leads, Add Card assigned to self, open own lead, change stage. | See/edit unassigned or other users' leads. | Partially Done | Pipeline > Add Card under stage > confirm assigned to S. Verma.
Counsellor | Follow-ups | Work assigned follow-ups. | Manage other users' follow-ups. | Partially Done | Create follow-up on own lead > complete/reschedule it.
Read-only | All CRM Views | View dashboard, leads, lead drawer, pipeline, follow-ups, reports. | Any create/edit/archive/assign/stage/follow-up/activity/master-data/user action. | Partially Done | Login R. Khanna > verify buttons disabled/hidden and API write attempts blocked.
Accountant | Payments | View lead payments; create/edit fees; record immutable transactions; view balances, statuses, receipts, and transaction history. | Access other tenants/inaccessible leads, overpay, duplicate receipts, cancel after a transaction, mutate archived leads, or bypass stale versions. | Ready for QA | Login as Accountant > open lead > add fee > record partial/final payment > test overpayment/duplicate receipt > verify cancellation and tenant boundaries.
Owner | Communication Templates | Create/edit/activate/deactivate templates, use placeholders, apply templates to any tenant lead. | Should not bypass duplicate name, version conflict, placeholder, or tenant boundaries. | Ready for QA | Settings > Communication Templates > add/edit duplicate/invalid placeholder tests > Lead drawer > apply template > confirm activity timeline.
Admin | Communication Templates | Create/edit templates and apply them to tenant leads within admin access. | Should not access platform-only areas or other tenants. | Ready for QA | Login admin > repeat template CRUD and lead drawer apply tests.
Counsellor | Communication Templates | View active templates in assigned lead drawer and apply them as activity logs. | Manage template CRUD, use inactive templates, or apply templates to inaccessible leads. | Ready for QA | Login S. Verma > open own lead > Use Communication Template > Apply > confirm timeline entry.
Read-only | Communication Templates | View lead timeline and settings data where permitted. | Create/edit templates or apply templates to leads. | Ready for QA | Login read-only > Settings should be view-only > Lead drawer template action should not be available.
Owner | Tenant Profile Settings | Edit institute profile, contact/address/timezone, branding, default branch, and default assignee. | Should not save invalid URLs/colors/timezones, inactive/cross-tenant defaults, or overwrite a newer version. | Ready for QA | Login Rahul > Settings > Institute Profile > edit/save > refresh > confirm sidebar identity > Add Lead > confirm branch/assignee defaults > test invalid fields and reset.
Admin | Tenant Profile Settings | Edit all tenant profile and lead-default fields inside the current tenant. | Access platform tenant controls, cross-tenant branches/users, or bypass version conflicts. | Ready for QA | Login Admin > repeat profile save and Add Lead default tests > confirm Platform remains unavailable.
Counsellor | Tenant Profile Settings | View current institute profile and branding. | Edit or save tenant profile/default settings; inherit another user as assignee when creating a lead. | Ready for QA | Login S. Verma > Settings > Institute Profile is read-only > Add Lead remains assigned to S. Verma.
Read-only | Tenant Profile Settings | View current institute profile and branding. | Edit/save profile or create a lead using defaults. | Ready for QA | Login R. Khanna > Settings > Institute Profile is read-only > verify no Save action and API update is blocked.
Owner | Lead Import/Export | Download templates, preview CSV/XLSX, correct mappings, commit clean rows, export filtered leads. | Should not bypass validation or import archived duplicate updates. | Ready for QA | Leads > Import > download template > preview valid/invalid file > commit clean rows > export CSV/XLSX with filters.
Admin | Lead Import/Export | Run the same tenant-scoped import/export workflow as owner. | Should not access platform data or other tenants. | Ready for QA | Login admin > Leads > Import/Export > verify tenant-only records and validation errors.
Counsellor | Lead Import/Export | Use normal lead creation/editing only. | Should not see import/export controls or call import/export APIs. | API boundary tested; UI QA pending | Login S. Verma > Leads should not show Import/Export; direct import template API returns 403.
Owner | Reports | View all tenant reports, filter by date/branch/course/source/counsellor, export CSV/XLSX. | Should not see cross-tenant data. | Ready for QA | Login Rahul > Reports > change filters > verify totals/tables/funnel > export CSV and XLSX.
Admin | Reports | View tenant reports and export CSV/XLSX within tenant scope. | Should not access platform/cross-tenant reports. | Ready for QA | Login admin > Reports > verify filters and exports match lead data.
Counsellor | Reports | View scoped reports for accessible/assigned leads. | Should not export reports or see all tenant-only data. | API boundary tested; UI QA pending | Login S. Verma > Reports > verify scoped totals > confirm export buttons hidden/direct export API returns 403.
Read-only | Reports | View reports without mutating data. | Should not export or edit data. | API view smoke tested; UI QA pending | Login R. Khanna > Reports > verify read-only view and no export controls.

## Sprint Plan
Sprint | Theme | Scope | Deliverables | Status | Do Not Start Until | Acceptance Criteria
Sprint 0 | Current Workflow Stabilization | Fix confusing UI around Leads filters, Pipeline Add Card, follow-up/activity drawer usability, role disabled states. | No dead buttons; key workflows testable by Owner/Counsellor/Read-only. | In Progress | Now | Manual role QA passes for existing features.
Sprint 1 | Activity Communication Templates | Template CRUD, variable placeholders, template picker in lead drawer, template-generated activity logs. | Templates API/table/migration, Settings CRUD UI, lead drawer template picker, placeholder rendering, and activity logging. | Partially Done | Sprint 0 | Builds pass, database migration is applied, and local owner smoke test returns seeded templates. Manual role QA must pass before moving Sprint 1 to Completed.
Sprint 2 | Tenant Profile Settings | Institute profile, logo/contact details, default branch/assignment preferences, persisted settings page. | Tenant profile APIs/UI, contact and address fields, timezone, logo URL, brand color, default branch/assignee, global tenant identity refresh, validation, and concurrency protection. | Partially Done | Implementation advanced by user direction; Sprint 1 and Sprint 2 QA gates remain. | Builds and migrations pass; Owner/Admin can save valid settings; invalid/stale/unauthorized requests are blocked; app branding and new-lead defaults update; manual role QA passes.
Sprint 3 | Follow-up Workspace | Make Follow-ups page actionable with filters and row actions. | Due/overdue/upcoming/completed/cancelled queue filters, search, priority filter, open lead, complete/cancel/reschedule from list. | Partially Done | Sprint 0 | Owner/Counsellor can run daily follow-up work from the Follow-ups page; read-only can view only. Manual role QA pending.
Sprint 4 | Lead Import/Export | CSV/XLSX import preview, validation, duplicate handling, export current filters. | CSV/XLSX template downloads, preview/mapping UI, validation issue list, duplicate skip/update behavior, atomic commit endpoint, activity logs, filtered CSV/XLSX export, Owner/Admin permissions. | Partially Done | Sprint 2 implementation complete; manual QA gates for Sprints 1-4 remain open. | Builds pass, owner can preview/export via API smoke, counsellor import is forbidden, and browser QA passes for template, preview, mapping, commit, duplicates, and export filters.
Sprint 5 | Reports Upgrade | Date filters, source/counsellor/stage analytics, exportable reports. | Reports API/UI with date, branch, course, source, counsellor filters; source/counsellor/stage tables; funnel; role-scoped data; CSV/XLSX export for Owner/Admin. | Partially Done | Sprint 4 implementation complete; manual QA gates for Sprints 1-5 remain open. | Builds pass, Owner/Admin can view/export reports, counsellor sees scoped reports and cannot export, read-only can view, and browser QA passes.
Sprint 6 | Documents | Document checklist, upload metadata, verification state. | Cloudinary document checklist, upload/replace, verification/rejection, download, deletion, permissions, and migration. | Partially Done | Sprint 5 | Implementation/build/migration complete; manual role QA and production Cloudinary environment configuration remain.
Sprint 7 | Payments | Fee records, payment status, due dates, receipts, accountant role behavior. | INR fee records, immutable transactions, balances/statuses, receipts, activity logs, accountant permissions, UI/APIs, and migration. | Partially Done | Sprint 6 | Implementation/build/migration complete; manual Owner/Admin/Accountant/Counsellor/Read-only QA remains.
Sprint 8 | Automation & Notifications | Provider-neutral background jobs, in-app reminders, follow-up/payment due notifications, delivery logs, retries/idempotency, email, then WhatsApp. | Hangfire PostgreSQL storage, notification/delivery schema, inbox UI, scheduling/dispatch services, provider adapters, observability, and tests. | Partially Done | Templates, follow-up workspace, and payment due-date implementation complete. | Phase 1 implementation/migration/API boundaries are marked complete; user deferred browser and live reminder tests. Email and WhatsApp remain later provider phases.
Sprint 9 | Production Release | Security, automated smoke tests, deployment pipeline, docs. | Production deployment to Render/Vercel/Neon. | Not Started | Core workflows QA pass | Production smoke test passes and secrets are rotated/configured.

## Sprint 8 Plan
Order | Workstream | Implementation Scope | Edge Cases / Production Controls | Exit Criteria | Current Status
1 | Decisions & Contracts | Define notification channels, event types, recipient rules, scheduling windows, provider-neutral interfaces, and configuration contracts. | Missing provider credentials must disable only that channel; validate timezone and quiet-hour rules; never put secrets in source. | Contracts and configuration validation are agreed; in-app channel can operate without external providers. | Implemented for in-app; external providers deferred
2 | Data Model & Migration | Add tenant-scoped notifications, delivery attempts, preferences, deduplication keys, scheduled time, status, retry count, and audit timestamps. | Unique tenant/event/recipient deduplication; immutable attempts; UTC storage; constrained statuses/channels; indexed pending-job queries; safe cascade behavior. | Migration applies to Neon and supports traceable notification lifecycle without cross-tenant access. | Implemented and applied to Neon
3 | Hangfire Infrastructure | Configure Hangfire with PostgreSQL storage, recurring scanners, queues, dashboard authorization, cleanup, and health checks. | Multi-instance locking; job timeouts; graceful restart; clock skew; poison jobs; retention; dashboard hidden from unauthorized users. | Jobs survive restarts, only one worker claims logical work, and health/queue state is observable. | Implemented and runtime initialized
4 | Reminder Scheduling | Create follow-up due, overdue, payment due, payment overdue, and optional stale-lead reminder producers. | Reschedule/cancel/completion invalidates stale reminders; archived leads suppressed; status rechecked at execution; timezone/DST handled; no duplicate reminders. | Each eligible business event creates exactly one current reminder and obsolete reminders do not send. | Implemented; disposable-data QA deferred by user
5 | In-App Notifications | Add role-scoped notification inbox, unread count, mark read/all read, deep links, pagination, and filters. | Deleted/inaccessible leads must not leak data; read operations tenant/user scoped; stale deep links degrade safely; large inbox remains paginated. | Users see only relevant notifications and can manage read state reliably. | Implemented; browser QA deferred by user
6 | Delivery Pipeline | Dispatch through channel adapters and record queued/sent/delivered/failed/skipped outcomes with sanitized provider responses. | Exponential backoff with jitter; max attempts; transient/permanent failure classification; idempotency keys; no retry after cancellation; payload size validation. | Retries are bounded, observable, and cannot create duplicate logical deliveries. | Implemented for in-app delivery; external channel delivery deferred
7 | Email Adapter | Add transactional email provider adapter, verified sender configuration, template rendering, and webhook-ready message IDs. | Invalid/missing email; provider outage/rate limit; bounced/complaint suppression; HTML escaping; secret rotation; timeout/circuit-breaking. | Email can be enabled by environment configuration and failures are recorded without blocking other channels. | Deferred next planned feature after Phase 1 QA/sign-off
8 | WhatsApp Adapter | Add behind a feature flag after provider/account/template approval; map approved templates and delivery statuses. | Opt-in/consent; approved-template enforcement; phone normalization; 24-hour conversation rules; provider rate limits; disabled-by-default configuration. | WhatsApp is isolated behind an adapter and feature flag with compliant templates and delivery tracking. | Deferred; keep disabled until compliant provider/templates are ready
9 | Permissions & Preferences | Owner/Admin configure tenant notification settings; users control allowed personal preferences where policy permits. | Mandatory operational alerts cannot be silently disabled; Accountant gets payment alerts only; Counsellor scope follows lead access; read-only cannot configure tenant settings. | Backend authorization and UI states match the role matrix and tenant boundaries. | Implemented; manual role QA deferred by user
10 | Observability & Security | Add structured logs, correlation IDs, metrics, redaction, health indicators, and operational failure views. | No secrets or sensitive document/payment payloads in logs; webhook signatures verified; rate limiting; replay protection; actionable alert thresholds. | Operators can diagnose failures without exposing tenant data or credentials. | Partially implemented; production alerts pending
11 | Testing & Rollout | Unit-test scheduling/idempotency, integration-test jobs/storage, API role tests, provider fakes, and staged feature-flag rollout. | DST boundaries; concurrent workers; retries; provider timeout; duplicate webhook; tenant isolation; reschedule/cancel races; database restart. | Automated critical-path tests pass; in-app launches first, email second, WhatsApp last; rollback disables channels without losing records. | API smoke passed; browser/disposable-data/load tests deferred by user

## Status Legend
Status | Meaning | Rule
Completed | Implemented and verified enough to treat as stable foundation. | Only minor polish or production hardening remains.
Partially Done | Useful implementation exists, but workflow, UX, coverage, or edge cases are incomplete. | Do not build dependent advanced features until gaps are clear.
Next Priority | The next feature to build after stabilizing the current workflows. | Should be started before lower-priority modules.
Not Started | No meaningful implementation yet. | Needs design, API, UI, validation, permissions, and tests.
Blocked/Needs Decision | Cannot proceed cleanly without product/technical decision. | Resolve decision before implementation.